## CHRONOLOGICAL CHECKLIST
Event Checklist
When | Task | Notes | Who? | Status
Start of project | ADMIN: Develop a Project Brief (Basics/Scope/Promotion Overview*)
Start of project | ADMIN: Identify resources required and Develop Budget
Start of project, Ongoing | ADMIN: Start budget spreadsheet and update throughout event
Start of project, ongoing | PROMOTION AND MARKETING: Develop Communication plan for event | Fill out a communications plan with list of dates and publications in which you wish to advertise or promote. Include website, social media, press releases, e-news. Appoint media liaison.
Start of project, ongoing | ADMIN: Contact list – listing all relevant stakeholders, roles and contact details
Start of project | ADMIN: Ensure that all involved have public liability insurance
Start of project | ADMIN: Complete Risk Assessment Checklist
Start of project | COMMUNITY ENGAGEMENT: Arrange schedule for regular team meetings with relevant stakeholders and provide regular status reports | meeting regularly with all stakeholders to confirm their tasks and activities, make clear your expectations of their contribution (speakers, performers, caterers, cleaners, printers, venue managers, govt authorities, police, emergency services, community reps etc)
Start of project | ADMIN: Set up online booking (if required) | Trybooking.com. Ensure that it contains photo consent form.
Start of project, Ongoing | ADMIN: Checklist – ensure this checklist is up to date and includes appropriate timelines.
Prior to 12 weeks out | VENUE: Conduct site visit and identify infrastructure, power and lighting requirements
12 weeks out | COMMUNITY ENGAGEMENT: Contact local businesses and community groups to become involved in the event
12 weeks out | VENUE: Book venue and fill out appropriate application / paperwork ensuring you get quotes and book any external service providers
12 weeks out | EVENT PROGRAM: Develop activities list/agenda/programming/schedule including artist register
11 weeks out with ongoing updates | VENUE: Prepare hire equipment list (tables, chairs, marquees/tents, AV equipment etc), booking any required for external service providers
11 weeks out | PROMOTION AND DOCUMENTATION: Graphic Design | Ensure message and design is consistent and accurate Flyer/Poster/Tickets/Invitations/Ads/Feedback Forms
10 weeks out | PROMOTION AND DOCUMENTATION: Determine if photographer required or if officer photography is sufficient, book photographer if necessary
10 weeks out | EVENT PROGRAM: Organise a Welcome to Country (if applicable)
10 weeks out | EVENT PROGRAM: Book and arrange for MC/Speakers, Artists and Special Guests | Travel, accom, letter of confirmation/contract, info package if needed with all bookings and fees. Template of agreement on ANW site.
10 weeks out | VENUE: Identify catering requirements for speakers, artists, volunteers, staff | Beverages (if alcoholic - need RSA licence) Food (need to comply with food safety legislation)
9 weeks out | VENUE: Get quotes from catering companies
8 weeks out with ongoing updates | ADMIN: Prepare an event run sheet outlining all the tasks for event set up, during event and event bump out
8 weeks out | PROMOTION AND DOCUMENTATION: Prepare invitation distribution list and ensure you include information about your wet weather contingency plans
8 weeks out | ADMIN: Obtain signed contract for artists/speakers – ensure contract is signed by both parties
8 weeks out | ADMIN: Identify and organise speaker / performer gifts (if required)
8 weeks out | VENUE: Catering - Confirm menus and prices
7 weeks out | ADMIN: Prepare a event signage list: Directional signage (toilets/no entry) /Promotional signage /Sponsor or partner signage/Program | Event and sponsor/partner logos.
6-8 weeks out | VENUE: Prepare site maps and arrange delivery times for catering and equipment
6 weeks out | COMMUNITY ENGAGEMENT: Advise local businesses and residents of the event, any road closures
6 weeks out | COMMUNITY ENGAGEMENT: Invite local Councillors, Federal and State Members to attend event (if relevant)
6 weeks out | PROMOTION AND DOCUMENTATION: Send out electronic and hard copy invitations
4 weeks out | EVENT PROGRAM: Contact Participants with update/reminder. If applicable, provide attendees with list of requirements, responsibilities, agenda or program (ask if they have any needs/requirements) | Email/print version of event and schedule
4 weeks out | EVENT PROGRAM: Prepare MC notes/script; notes for guest speakers (if required)
4 weeks out | VENUE: Order and / or print remaining signage
2 weeks out | VENUE: Arrange for collection of keys / swipe cards and after hours access if required
2 weeks out | PROMOTION AND DOCUMENTATION: Print out feedback forms.
2 weeks out | VENUE: Confirm final numbers for catering, and confirm delivery times/places
2 weeks out | EVENT PROGRAM: To speakers/artists/ Send through notes, event brief, map and run sheet
1 week out | ADMIN: Print out participant lists, and note whether all have signed photo consent form
1 week out | VENUE: Conduct final site visit
1 week out | VENUE: Collect existing signage
1 week out | ADMIN: Print event run sheet for staff | Print sheet for management with delegated tasks and timeline
DURING | PROMOTION AND DOCUMENTATION: Record and document event - staff photographer or external provider
DURING | PROMOTION AND DOCUMENTATION: Distribute and collect feedback forms
Post event | ADMIN: Restock all event boxes
Post event | PROMOTION AND DOCUMENTATION: Upload photos etc onto dropbox or file accordingly
Post event | PROMOTION AND DOCUMENTATION: Arrange debrief with event staff and other relevant stakeholders involved | Analysis - how did event go? What went well? What could we do beter?
Post event | ADMIN: Write thankyou letters / emails and send to all stakeholders, contributors, donors/sponsors, volunteers and other relevant event staff
Post event | ADMIN: Ensure all invoices are received, reconciled and paid, bank any income
Post event | ADMIN: Prepare financial statement of actuals v budget.
Post event | PROMOTION AND DOCUMENTATION: Final event report and acquittal

## SORTED UNDER AREAS CHECKLIST
Event Checklist
Task | Notes | When | Who? | Status
ADMIN: Develop a Project Brief (Basics/Scope/Promotion Overview*) |  | Start of project
ADMIN: Identify resources required and Develop Budget |  | Start of project
ADMIN: Start budget spreadsheet and update throughout event |  | Start of project, Ongoing
ADMIN: Contact list – listing all relevant stakeholders, roles and contact details |  | Start of project, ongoing
ADMIN: Ensure that all involved have public liability insurance |  | Start of project
ADMIN: Complete Risk Assessment Checklist |  | Start of project
ADMIN: Set up online booking (if required) | Trybooking.com. Ensure that it contains photo consent form. | Start of project
ADMIN: Checklist – ensure this checklist is up to date and includes appropriate timelines. |  | Start of project, Ongoing
ADMIN: Prepare an event run sheet outlining all the tasks for event set up, during event and event bump out |  | 8 weeks out with ongoing updates
ADMIN: Obtain signed contract for artists/speakers – ensure contract is signed by both parties |  | 8 weeks out
ADMIN: Identify and organise speaker / performer gifts (if required) |  | 8 weeks out
ADMIN: Prepare a event signage list: Directional signage (toilets/no entry) /Promotional signage /Sponsor or partner signage/Program | Event and sponsor/partner logos. | 7 weeks out
ADMIN: Print out participant lists, and note whether all have signed photo consent form |  | 1 week out
ADMIN: Print event run sheet for staff | Print sheet for management with delegated tasks and timeline | 1 week out
ADMIN: Restock all event boxes |  | Post event
ADMIN: Write thankyou letters / emails and send to all stakeholders, contributors, donors/sponsors, volunteers and other relevant event staff |  | Post event
ADMIN: Ensure all invoices are received, reconciled and paid, bank any income |  | Post event
ADMIN: Prepare financial statement of actuals v budget. |  | Post event
VENUE: Conduct site visit and identify infrastructure, power and lighting requirements |  | Prior to 12 weeks out
VENUE: Book venue and fill out appropriate application / paperwork ensuring you get quotes and book any external service providers |  | 12 weeks out
VENUE: Prepare hire equipment list (tables, chairs, marquees/tents, AV equipment etc), booking any required for external service providers |  | 11 weeks out with ongoing updates
VENUE: Identify catering requirements for speakers, artists, volunteers, staff | Beverages (if alcoholic - need RSA licence) Food (need to comply with food safety legislation) | 10 weeks out
VENUE: Get quotes from catering companies |  | 9 weeks out
VENUE: Catering - Confirm menus and prices |  | 8 weeks out
VENUE: Prepare site maps and arrange delivery times for catering and equipment |  | 6-8 weeks out
VENUE: Order and / or print remaining signage |  | 4 weeks out
VENUE: Arrange for collection of keys / swipe cards and after hours access if required |  | 2 weeks out
VENUE: Confirm final numbers for catering, and confirm delivery times/places |  | 2 weeks out
VENUE: Conduct final site visit |  | 1 week out
VENUE: Collect existing signage |  | 1 week out
COMMUNITY ENGAGEMENT: Arrange schedule for regular team meetings with relevant stakeholders and provide regular status reports | meeting regularly with all stakeholders to confirm their tasks and activities, make clear your expectations of their contribution (speakers, performers, caterers, cleaners, printers, venue managers, govt authorities, police, emergency services, community reps etc) | Start of project
COMMUNITY ENGAGEMENT: Contact local businesses and community groups to become involved in the event |  | 12 weeks out
COMMUNITY ENGAGEMENT: Advise local businesses and residents of the event, any road closures |  | 6 weeks out
COMMUNITY ENGAGEMENT: Invite local Councillors, Federal and State Members to attend event (if relevant) |  | 6 weeks out
PROMOTION AND MARKETING: Develop Communication plan for event | Fill out a communications plan with list of dates and publications in which you wish to advertise or promote. Include website, social media, press releases, e-news. Appoint media liaison. Don’t forget ANW Calendar | Start of project, ongoing
PROMOTION AND DOCUMENTATION: Graphic Design | Ensure message and design is consistent and accurate Flyer/Poster/Tickets/Invitations/Ads/Feedback Forms | 11 weeks out
PROMOTION AND DOCUMENTATION: Determine if photographer required or if officer photography is sufficient, book photographer if necessary |  | 10 weeks out
PROMOTION AND DOCUMENTATION: Prepare invitation distribution list and ensure you include information about your wet weather contingency plans |  | 8 weeks out
PROMOTION AND DOCUMENTATION: Send out electronic and hard copy invitations |  | 6 weeks out
PROMOTION AND DOCUMENTATION: Print out feedback forms. |  | 2 weeks out
PROMOTION AND DOCUMENTATION: Record and document event - staff photographer or external provider |  | DURING
PROMOTION AND DOCUMENTATION: Distribute and collect feedback forms |  | DURING
PROMOTION AND DOCUMENTATION: Upload photos etc onto dropbox or file accordingly |  | Post event
PROMOTION AND DOCUMENTATION: Arrange debrief with event staff and other relevant stakeholders involved | Analysis - how did event go? What went well? What could we do beter? | Post event
PROMOTION AND DOCUMENTATION: Final event report and acquittal |  | Post event
EVENT PROGRAM: Contact Participants with update/reminder. If applicable, provide attendees with list of requirements, responsibilities, agenda or program (ask if they have any needs/requirements) | Email/print version of event and schedule | 4 weeks out
EVENT PROGRAM: Prepare MC notes/script; notes for guest speakers (if required) |  | 4 weeks out
EVENT PROGRAM: Organise a Welcome to Country (if applicable) |  | 10 weeks out
EVENT PROGRAM: Book and arrange for MC/Speakers, Artists and Special Guests | Travel, accom, letter of confirmation/contract, info package if needed with all bookings and fees. Template of agreement on ANW site. | 10 weeks out
EVENT PROGRAM: Develop activities list/agenda/programming/schedule including artist register |  | 12 weeks out
EVENT PROGRAM: To speakers/artists/ Send through notes, event brief, map and run sheet |  | 2 weeks out